## Risk Register
Geothermal Well Drilling Risk Register
Well: | Geothermal |  | Risk Register Owner: | Akram Miriyev | [5 empty] | Last Updated: | 2026-06-23
|  |  |  | Analyzed Offset Wells | BLT-01, ADK-GT-01/02, KKP-GT-01, WSP-01, ERM-01, ALE-01, HEK-GT-01-S2
Step 1. Identify and categorize the Risk Event | [5 empty] | Step 2. Assess Risk Ranking |  | Step 3. Identify Risk Management Measures |  |  | Step 4. Assess Net Ranking
Risk No | Risk Event | Consequence | Category | Risk Type / Solution | Owner | Worst Credible Assessment |  | Observed on Specific Offset Wells* | Formation / Lithology | Prevention / Mitigations | Net Assessment |  | Matrix Helper
[6 empty] | Likelihood of Occurrence | Impact |  |  |  | Residual Likelihood of Occurrence | Residual Impact | Selected Likelihood | Selected Impact | Slot in Quadrant | Matrix Key
1 | Losses while drilling | Unable to drill ahead and /or Unable to trip due to heavy losses | All Types of Wells | Operations |  | 5 | C | 1. BLT-01 - Observed losses during drilling 8.5" section - partial success achieved multiple LCM pill placement. Eventually losses stopped. Run & cement 7" liner without any losses. 2. ADK-GT-01 : Dynamic losses at 230m were recorded in a rate of 10 m³/h decreased to 8 m³/h dynamic losses at 270 m after pumping Lcm. Between 225m-275m total losses was recorded, in total 88 m³ was lost. In 24" section losses (dynamic) ca. 88 m³ Static losses at 515 m 0.3 m³/h was reported when top of marl of Oosterhout formation was drilled.- North Sea formation is naturally more permeable. If the rock formations have high porosity (e.g., sandstone or fractured rock), drilling fluid (mud) can easily flow into these porous zones, causing mud loss. No detailed information were mentioned in the reports about the cause of the losses. 3. ADK-GT-02 : Mud losses were reported between depths of 140m and 280m, with dynamic losses ranging from 15 to 25 m³/h. At 235m, static losses were recorded at 200 l/h, leading to a total of 65m³ of losses per day. By the end of the day, the cumulative mud losses amounted to 250m³. However, after reaching a depth of 280m, no further mud losses were observed.-The cause of the losses are possibly by high permeable unconsolidated sediments of Upper North sea. | 1. Zechstein Upper Claystone and Z4 2. NUOT 3. NUCT | LCM strategy ready, Optimized filter cake, Mud weight management (differential sticking) | 4 | D | 4 | D | 1 | 4¦D¦1
2 | Issues while sliding with motor (oriented drilling) | Deviation from plan, Loss of steerability | Highly-deviated | Operations |  | 2 | D |  |  | Ensure proper hole cleaning by adequate mud properties, Trained personnel, Optimised trajectory using latest directional trajectory, Continuously control survey, QC equipment | 1 | E | 1 | E | 1 | 1¦E¦1
3 | High wellbore tortuosity, high local doglegs | High torque and drag levels further down the hole, Issues placing the ESP, | Highly-deviated | Planning |  | 4 | E |  |  | Watch out for transition zones, Do not exceed a recommended level dogleg ~3 deg/30m dogleg unless consequences thoroughly analyzed. Wash and ream high doglegs carefully, Trained personnel, Optimised trajectory, Continuously control survey, QC equipment | 2 | F | 2 | F | 1 | 2¦F¦1
4 | Poor Directional control , inability to follow directional plan for BHA or formation related issues | Additional BHA trips, loss of rig time. Reduced ROP to achieve required steering capabilities Poor hole quality and high well tortuosity if the wrong directions are not corrected on time. | Highly-deviated | Operations |  | 5 | D | 1. KKP-GT-01 : While drilling 12 1/4" BHA trip was required to establish required build rate. New BHA drilled to section TD. 2. WSP-01 : While drilling the 12 1/4"section some deviation problems were encountered in the Jurassic shales which slowed down penetration rates considerably.-No details on cause of deviation problems were reported. They may be inflicted by layering of shales. | 1. NLLFC 2. ATAL | In case of restrictions adjust parameters while reaming, Low RPM and low flow, Avoid reaming down, Trained personnel, Optimised trajectory, Continuously control survey, QC equipment | 4 | E | 4 | E | 1 | 4¦E¦1
5 | Hole instability Issues | Tight hole, Loss of hole, Running casing to bottom | All Types of Wells | Planning |  | 5 | C | ADK-GT-01 : The geological report and mud logging indicated that the Vlieland claystone appeared unstable while drilling with a 1.30 s.g. mud weight (MW). After increasing the mud weight to 1.35 s.g., fewer overpulls and cavings were observed.-It was observed that the Vlieland claystone was unstable with an insufficient mud weight of 1.30 s.g., and showed improved stability when the mud weight was increased to 1.35 s.g. | KNNC / Vlieland Claystone Formation | Carry out geomechanical study for the specific well. Analyze offset wells' cuttings report, losses and FITs to select suitable MWs. Monitor returns and adjust mud weight as required, Ensure proper hole cleaning and mud inhibition, Ream as and when required | 4 | E | 4 | E | 2 | 4¦E¦2
6 | Pack offs around BHA while drilling shoetrack or connection | Stuck pipe, Loss of circulation, Loss of equipment | All Types of Wells | Planning |  | 5 | E |  |  | Monitor string up and down weights carefully, special care when picking up, Monitor trends i.e., torque, ECD, SPP, cuttings, Ensure correct mud parameters and inhibition | 4 | G | 4 | G | 1 | 4¦G¦1
7 | Losses during cement job | Integrity problems, Cross flow, Ground water pollution | All Types of Wells | Operations |  | 4 | D |  |  | Optimised cement weight, schedule and pumping, ECD monitoring, Use LC fibres, Maintain mud properties, Check for incompatibility, Prepare spaghetti pipes in anulus and cement | 3 | E | 3 | E | 1 | 3¦E¦1
8 | Shock & Vibrations While Drilling | Damage to high cost BHA items, lost in hole, BHA twist-off or BHA back-off due to reactive torque. Time consuming fishing operations to fish BHA items. | All Types of Wells | Operations |  | 4 | E | ERM-01 : Drill string broke while drilling the 12 1/4" hole section. Multiple fishing attempts but these did not solve the problem. Sidetrack was required.-Stuck pipe possibly due to swelling clays in sandy claystone. | NM | Monitoring drilling fluid, Set up parameters and ranges by mud engineer, Keep in contact with WSG | 3 | F | 3 | F | 1 | 3¦F¦1
9 | Previous section not TD'ed according to plan, shallow set previous casing | Break out of unstable clay or porous sandstone | All Types of Wells | Operations |  | 2 | D |  |  | Mud properties to adapt to drilling the unplanned section. Carry out KT calculations to ensure if next hole section can be drilled with min required KT volume. Continuous monitoring and control on cavings and formation type, | 1 | F | 1 | F | 1 | 1¦F¦1
10 | Kick while drilling / Well Control | Time delay, Break down of 185/8" shoe, Environmental impact, Human injuries | All Types of Wells | Operations |  | 5 | A |  |  | Use of proper Well control equipment, and regular pressure testing according to industry standards. Trained personnel, Kick detection system, continous well monitoring procedures. Ensure having enough weighting material on site to increase mud density | 4 | C | 4 | C | 1 | 4¦C¦1
11 | Leaking liner top packer | Well integrity issues | All Types of Wells | Operations |  | 2 | C |  |  | Test packer/ liner lap upon installation, Ensure contingency tie-back packer available if liner lap is leaking, Scraping 9-5/8" casing prior to liner run, trained personnel for liner hanger/packer setting operations | 1 | D | 1 | D | 1 | 1¦D¦1
12 | Total losses (i.e no returns) | Loosing BHA and equipment, Fractures, Resulting side track, Loss of well control, Loss of well integrity | All Types of Wells | Operations |  | 4 | C |  |  | Preparation of loss decision tree to decide which LCM material to use (LCM strategy) Preparation of cement plugs, Optimize mud and cement weights including fibres | 3 | D | 3 | D | 1 | 3¦D¦1
13 | Insufficient FIT | Insufficient kick tolerance | All Types of Wells | Operations |  | 2 | D |  |  | Consider accepting low FIT and drill ahead with limited parameters - analyze risk of poor hole cleaning and loss of directional control. Have cement stinger and cement recipe available to perform cement squeeze of casing shoe. | 1 | E | 1 | E | 2 | 1¦E¦2
14 | Not able to run casing or liner to bottom | Time delay, Change of casing seat, Operational issues in next section | All Types of Wells | Operations |  | 2 | E |  |  | Consider check-trip to shoe if poor hole condition suspected. Clear backreaming practices. Monitoring hole conditions while POOH with BHA, Monitoring torque and drag, Avoid high doglegs, | 1 | F | 1 | F | 2 | 1¦F¦2
15 | Differential Stuck Pipe | Sticking the 21-1/2" BHA, delay, lost BHA | All Types of Wells | Operations |  | 5 | C |  |  | Minimize Differential Pressure Across Permeable Zones Minimize Static Time in Vulnerable Zones Optimize Mud System & Filter Cake Quality Use special downhole tools to reduce contact area (spirotorqs) | 5 | D | 5 | D | 1 | 5¦D¦1
16 | Shallow gas | Uncontrolled gas flow at surface, fire at rig and loss of personnel life | All Types of Wells | Planning |  | 2 | B |  |  | Conduct shallow hazard surveys (seismic, offset well analysis) to identify potential shallow gas zones and plan casing depths accordingly. Set conductor and surface casing below all identified/suspected shallow gas zones with adequate cement to surface. Install and function-test diverter system immediately after conductor, with vent lines directed to safe burn pit/flare area away from rig. Maintain active gas detection (mud logger, pit-level sensors) from spud, with low threshold alarms for shallow formations. | 2 | C | 2 | C | 1 | 2¦C¦1
17 | Unable to circulate through shoe | Unable to cement, time delay | All Types of Wells | Operations |  | 3 | F |  |  | ensure ability to circulate through shoe prior running casing running. Break circulation while RIH at regularly if possible. Avoid using flat bottom or easy-to-plug shoe types. Lipstick shoes are generally better. | 2 | G | 2 | G | 1 | 2¦G¦1
18 | Well proposal does not describe in detail the potential geothermal well objectives | Well design may not be optimal for geothermal well lifecycle loads Limitations to injection operations, well life, injection / production rates, may result in cost increase. | All Types of Wells | Planning |  | 2 | E |  |  | Team to be aware of dual purpose, seek knowledge and available information about industry experience and recommendations. Clear understanding and alignment on primary objective of the well and walk-away scenario for certain subsurface related risks. | 2 | G | 2 | G | 2 | 2¦G¦2
19 | Well control due to PPFG uncertainty and limited data from off-set wells | Loss of well control, failure of barriers while drilling | All Types of Wells | Planning |  | 3 | B |  |  | Offset well analysis to enhance understanding of PPFG in the area. Robust casing design and mud weight design. Carry out section specific risk assessment with multi-disciplinary team for critical hole sections. | 2 | C | 2 | C | 2 | 2¦C¦2
20 | Incorrect geological identification of shoedepth | Shoe is set too shallow may result in hole stability issues Shoe set too deep may cause lack of core from seal section | All Types of Wells | Planning |  | 3 | F |  |  | Controlled ROP GR correlation and comparison to off-set wells Close sampling and inspection of cuttings | 2 | H | 2 | H | 1 | 2¦H¦1
21 | Top of cement not achieved as per planned | Integrity problems, Time delay | All Types of Wells | Operations |  | 5 | D |  |  | Optimise cement weights, schedule and pumping ECD monitoring, Maintain mud properties, Add loss circulation material to slurry Comprehensive slurry testing prior executing job, Have contingency equipment for top cement job on site (if possible) | 5 | E | 5 | E | 1 | 5¦E¦1
22 | Down hole LWD / MWD tool failure | Additional round trips, Time dependent hole stability issues Time delay, Poor data, Hole exposure, Poor directional control | All Types of Wells | Operations |  | 2 | D |  |  | Have complete back up, DHM and MWD available at site, Shallow hole test, Test tools on deck, Checking history and maintenance | 1 | F | 1 | F | 3 | 1¦F¦3
23 | Wireline logging failure/stuck tool | Lack of data for seismic well tie and geomechanics for overburden seal | Highly-deviated | Operations |  | 4 | C | KKP-GT-01: While logging the 12 1/4"section the logging tools stood up at 1055m (+/- 65 m from bottom). However zones of interest were succesfully logged. KKP-GT-01: While logging the 8 1/2"section the logging tools stood up at 1741m, therefore the ZeZC1 could not be logged. As a result gas in the ZeZC1 could not be excluded and the cement recipe of the 7"liner needed to be altered. | NLLFC KNGLM / Middle Holland Claystone Member | RIH simulation with service company's proprietary software - clear understanding of well geometry and high dogleg areas throughout the well. Have backup tool in case of failure, have fishing tools available if stuck in hole, condition of mud before logging, Perform hole condition trip with BHA Consider using rollers or tractor if well inclination has more than 60 deg. | 3 | E | 3 | E | 2 | 3¦E¦2
24 | Stuck casing | Time delay, Change of casing seat, Operational issues in next section, Space out problems at surface | All Types of Wells | Operations |  | 3 | B | KKP-GT-01: During the 7" liner installation it was not possible to reach planned setting gepth. The initial hold up depth was at 2091 m ah. Liner was washed down to 2097m ah where no progress was made. Decision was made cement liner in place. | ZEZ1C | Torque and drag analysis with emphasis on tripping out loads in case required. Monitor hole conditions on trip out prior to running casing Maintain mud properties to avoid differential sticking Consider hole condition check trip prior to casing run, Have water bushing available on site | 2 | C | 2 | C | 3 | 2¦C¦3
25 | Core barrel stuck / jamming | Fishing for core barrel, in worst case plug and sidetrack. | All Types of Wells | Operations |  | 2 | F | WSP-01 : Slow progress while coring in the 8 1/2"hole section as the fractured nature of the dolomite caused considerable core jamming-Jamming caused by fractured limestone | ZEZ3C | Have additional core barrels available Be prepared for side wall coring | 1 | H | 1 | H | 1 | 1¦H¦1
26 | Reservoir damage due to inappropriate drilling fluids | Incorrect or poor data during formation flow test which is critical to storage development plan, Potential poor/incorrect permeability data from WL and core data | All Types of Wells | Planning |  | 4 | E |  |  | Control mud weight and properties Avoid damaging products in mud Return permeability tests if possible using parameters from offset wells | 3 | G | 3 | G | 1 | 3¦G¦1
27 | Junction Integrity Risk | The junction creation and integrity are critical and technically complicated, posing significant risks during construction and operations, including potential blowout conditions. | Multilateral | Planning |  | 5 | B |  |  | Select the junction type based on pressure, life-of-well, and re-entry requirements; perform detailed pre-job engineering for casing, window milling, orientation, and loads; use qualified completion/junction systems; apply strict QA/QC during milling, running, cementing, and installation; verify integrity with pressure tests, inflow tests, cement evaluation, and drift/gauge runs; maintain clear primary and secondary well barriers; and limit aggressive operations near the junction while defining maximum allowable future mechanical loads. | 4 | C | 4 | C | 2 | 4¦C¦2
28 | Well Control Risk [Multilateral] | The complexity of multilateral wells can complicate well control, especially when running screens or slotted liners without an inner string, which can restrict circulation and lead to underbalanced situations. | Multilateral | Planning |  | 5 | A |  |  | Prepare a multilateral-specific well control plan for drilling, completion, re-entry, and intervention; model hydraulics and surge/swab pressures for each branch; | 4 | B | 4 | B | 1 | 4¦B¦1
29 | Task-Performance Risk | High-risk areas include the physical building of the junction, drilling of the lateral, hydraulic fracturing, and operations near the junction, which can jeopardize the integrity of the well and production from all laterals. | Multilateral | Planning |  | 4 | D |  |  | Break the project into critical operations with formal risk assessments (for example HAZID/HAZOP); use experienced multilateral personnel and vendors; check BHA and tool compatibility for junction passage and lateral entry; | 3 | E | 3 | E | 3 | 3¦E¦3
30 | Fluid Management Risk | When re-entering the main well bore after completing the lateral, the condition of the fluid in the main bore is unknown, which can lead to underbalanced situations if there are leaks. | Multilateral | Planning |  | 5 | E |  |  | Before re-entry, circulate and condition fluids where possible and confirm density, rheology, solids, and gas contamination; monitor for losses, gains, pressure anomalies, and fluid-level changes; use temporary isolation devices or fluid barriers between zones; | 4 | F | 4 | F | 1 | 4¦F¦1
31 | Operational Time Risk | The time exposed to drilling mud can destabilize formations, particularly in shale or depleted reservoirs, leading to potential borehole collapse or sticking of tools during logging operations. | Multilateral | Planning |  | 5 | E |  |  | Reduce open-hole exposure through optimized sequencing, trip planning, and logistics; select drilling fluids with strong shale inhibition and fluid-loss control; continuously update the wellbore stability model using real-time data; | 4 | G | 4 | G | 2 | 4¦G¦2
32 | Tight spot in OH either due to chemical or mechanical borehole instability | Loss of time, stuck BHA, loss of of the BHA, plug&abandon | All Types of Wells | Operations |  | 3 | D | ALE-01 : While making a check trip in the 17 1/2"hole section prior to logging a bridge was encountered at 687m, bridge was cleared. While logging the Induction-SP log could not pass 465m. A check trip was made and the section 465-660m was reamed. On second attempt the Induction-SP log would not pass 746m, resulting in bottom part of the hole not being logged. | Breda / NUBA |  | 2 | F | 2 | F | 2 | 2¦F¦2
33 | Bit related issues : Bit balling, bit wear | Additional trips to change out bit, reduction in ROP, loss of time. | All Types of Wells | Planning |  | 3 | E | HEK-GT-01-S2 : 12 1/4” Hole: Volpriehausen sandstone is hard and abrasive due to which bit wears out fast and is undergauge with as result slow ROP. -The Volpriehausen sandstone formation is hard and abrasive, causing rapid bit wear. As the bit wears out quickly, it becomes undergauge, which leads to slower Rate of Penetration (ROP). This results in reduced drilling efficiency and increased time required to drill through the formation. | RBMVL | Analysis of offset wells, adhere to the regional bit selection guide, section or formation specific bit designs could also prevent unexpected bit issues. During operations monitor MSE (mechanical specific energy) to ensure bit not spending excess energy to drill-out unit volume of rock. | 2 | G | 2 | G | 3 | 2¦G¦3
34 | [12 empty] | 0 | 0 | 1 | 0¦0¦1
35 | [12 empty] | 0 | 0 | 2 | 0¦0¦2
36 | [12 empty] | 0 | 0 | 3 | 0¦0¦3
37 | [12 empty] | 0 | 0 | 4 | 0¦0¦4
38 | [12 empty] | 0 | 0 | 5 | 0¦0¦5
39 | [12 empty] | 0 | 0 | 6 | 0¦0¦6
40 | [12 empty] | 0 | 0 | 7 | 0¦0¦7
41 | [12 empty] | 0 | 0 | 8 | 0¦0¦8
42 | [12 empty] | 0 | 0 | 9 | 0¦0¦9
43 | [12 empty] | 0 | 0 | 10 | 0¦0¦10
44 | [12 empty] | 0 | 0 | 11 | 0¦0¦11
45 | [12 empty] | 0 | 0 | 12 | 0¦0¦12
46 | [12 empty] | 0 | 0 | 13 | 0¦0¦13
47 | [12 empty] | 0 | 0 | 14 | 0¦0¦14
48 | [12 empty] | 0 | 0 | 15 | 0¦0¦15
49 | [12 empty] | 0 | 0 | 16 | 0¦0¦16
50 | [12 empty] | 0 | 0 | 17 | 0¦0¦17
51 | [12 empty] | 0 | 0 | 18 | 0¦0¦18
52 | [12 empty] | 0 | 0 | 19 | 0¦0¦19
53 | [12 empty] | 0 | 0 | 20 | 0¦0¦20
54 | [12 empty] | 0 | 0 | 21 | 0¦0¦21
55 | [12 empty] | 0 | 0 | 22 | 0¦0¦22
56 | [12 empty] | 0 | 0 | 23 | 0¦0¦23
57 | [12 empty] | 0 | 0 | 24 | 0¦0¦24
58 | [12 empty] | 0 | 0 | 25 | 0¦0¦25
59 | [12 empty] | 0 | 0 | 26 | 0¦0¦26
60 | [12 empty] | 0 | 0 | 27 | 0¦0¦27
61 | [12 empty] | 0 | 0 | 28 | 0¦0¦28
62 | [12 empty] | 0 | 0 | 29 | 0¦0¦29
63 | [12 empty] | 0 | 0 | 30 | 0¦0¦30
64 | [12 empty] | 0 | 0 | 31 | 0¦0¦31
65 | [12 empty] | 0 | 0 | 32 | 0¦0¦32
66 | [12 empty] | 0 | 0 | 33 | 0¦0¦33
67 | [12 empty] | 0 | 0 | 34 | 0¦0¦34
68 | [12 empty] | 0 | 0 | 35 | 0¦0¦35
69 | [12 empty] | 0 | 0 | 36 | 0¦0¦36
70 | [12 empty] | 0 | 0 | 37 | 0¦0¦37
71 | [12 empty] | 0 | 0 | 38 | 0¦0¦38
72 | [12 empty] | 0 | 0 | 39 | 0¦0¦39
73 | [12 empty] | 0 | 0 | 40 | 0¦0¦40
74 | [12 empty] | 0 | 0 | 41 | 0¦0¦41
75 | [12 empty] | 0 | 0 | 42 | 0¦0¦42
76 | [12 empty] | 0 | 0 | 43 | 0¦0¦43
77 | [12 empty] | 0 | 0 | 44 | 0¦0¦44
78 | [12 empty] | 0 | 0 | 45 | 0¦0¦45
79 | [12 empty] | 0 | 0 | 46 | 0¦0¦46
80 | [12 empty] | 0 | 0 | 47 | 0¦0¦47
81 | [12 empty] | 0 | 0 | 48 | 0¦0¦48
82 | [12 empty] | 0 | 0 | 49 | 0¦0¦49
83 | [12 empty] | 0 | 0 | 50 | 0¦0¦50
84 | [12 empty] | 0 | 0 | 51 | 0¦0¦51
85 | [12 empty] | 0 | 0 | 52 | 0¦0¦52
86 | [12 empty] | 0 | 0 | 53 | 0¦0¦53
87 | [12 empty] | 0 | 0 | 54 | 0¦0¦54
88 | [12 empty] | 0 | 0 | 55 | 0¦0¦55
89 | [12 empty] | 0 | 0 | 56 | 0¦0¦56
90 | [12 empty] | 0 | 0 | 57 | 0¦0¦57
91 | [12 empty] | 0 | 0 | 58 | 0¦0¦58
92 | [12 empty] | 0 | 0 | 59 | 0¦0¦59
93 | [12 empty] | 0 | 0 | 60 | 0¦0¦60
94 | [12 empty] | 0 | 0 | 61 | 0¦0¦61
95 | [12 empty] | 0 | 0 | 62 | 0¦0¦62
96 | [12 empty] | 0 | 0 | 63 | 0¦0¦63
97 | [12 empty] | 0 | 0 | 64 | 0¦0¦64
98 | [12 empty] | 0 | 0 | 65 | 0¦0¦65
99 | [12 empty] | 0 | 0 | 66 | 0¦0¦66
100 | [12 empty] | 0 | 0 | 67 | 0¦0¦67

## Risk Matrix
Geothermal Well Drilling Risk Matrix
Well or Rig Name: | GEO4ALL
Worst Credible / Net Assessment: | Net Assessment
Geothermal Wells Risk Matrix - GEO4ALL - Net Assessment
Net Assessment Likelihood
|  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  | 5 | 6 | 7 | 8 | # | Key Risk Short Title
| Net Assessment Impact | A | [15 empty] | 1 | Losses while drilling
[18 empty] | 2 | Issues while sliding with motor (oriented drilling)
[18 empty] | 3 | High wellbore tortuosity, high local doglegs
[18 empty] | 4 | Poor Directional control , inability to follow directional plan for BHA or formation related issues
[18 empty] | 5 | Hole instability Issues
|  | B | [9 empty] | 28 | [5 empty] | 6 | Pack offs around BHA while drilling shoetrack or connection
[18 empty] | 7 | Losses during cement job
[18 empty] | 8 | Shock & Vibrations While Drilling
[18 empty] | 9 | Previous section not TD'ed according to plan, shallow set previous casing
[18 empty] | 10 | Kick while drilling / Well Control
|  | C |  |  |  | 16 | 19 | 24 |  |  |  | 10 | 27 |  |  |  |  | 11 | Leaking liner top packer
[18 empty] | 12 | Total losses (i.e no returns)
[18 empty] | 13 | Insufficient FIT
[18 empty] | 14 | Not able to run casing or liner to bottom
[18 empty] | 15 | Differential Stuck Pipe
|  | D | 11 | [5 empty] | 12 |  |  | 1 |  | 15 |  |  |  | 16 | Shallow gas
[18 empty] | 17 | Unable to circulate through shoe
[18 empty] | 18 | Well proposal does not describe in detail the potential geothermal well objectives
[18 empty] | 19 | Well control due to PPFG uncertainty and limited data from off-set wells
[18 empty] | 20 | Incorrect geological identification of shoedepth
|  | E | 2 | 13 |  |  |  |  | 7 | 23 | 29 | 4 | 5 | 21 |  |  |  | 21 | Top of cement not achieved as per planned
[18 empty] | 22 | Down hole LWD / MWD tool failure
[18 empty] | 23 | Wireline logging failure/stuck tool
[18 empty] | 24 | Stuck casing
[18 empty] | 25 | Core barrel stuck / jamming
|  | F | 9 | 14 | 22 | 3 | 32 |  | 8 |  |  | 30 | [5 empty] | 26 | Reservoir damage due to inappropriate drilling fluids
[18 empty] | 27 | Junction Integrity Risk
[18 empty] | 28 | Well Control Risk [Multilateral]
[18 empty] | 29 | Task-Performance Risk
[18 empty] | 30 | Fluid Management Risk
|  | G |  |  |  | 17 | 18 | 33 | 26 |  |  | 6 | 31 |  |  |  |  | 31 | Operational Time Risk
[18 empty] | 32 | Tight spot in OH either due to chemical or mechanical borehole instability
[18 empty] | 33 | Bit related issues : Bit balling, bit wear
[18 empty] | 34 | 0
[18 empty] | 35 | 0
|  | H | 25 |  |  | 20 | [11 empty] | 36 | 0
[18 empty] | 37 | 0
[18 empty] | 38 | 0
[18 empty] | 39 | 0
[18 empty] | 40 | 0
[18 empty] | 41 | 0
[18 empty] | 42 | 0
[18 empty] | 43 | 0
[18 empty] | 44 | 0
[18 empty] | 45 | 0
[18 empty] | 46 | 0
[18 empty] | 47 | 0
[18 empty] | 48 | 0
[18 empty] | 49 | 0
[18 empty] | 50 | 0
[18 empty] | 51 | 0
[18 empty] | 52 | 0
[18 empty] | 53 | 0
[18 empty] | 54 | 0
[18 empty] | 55 | 0
[18 empty] | 56 | 0
[18 empty] | 57 | 0
[18 empty] | 58 | 0
[18 empty] | 59 | 0
[18 empty] | 60 | 0
[18 empty] | 61 | 0
[18 empty] | 62 | 0
[18 empty] | 63 | 0
[18 empty] | 64 | 0
[18 empty] | 65 | 0
[18 empty] | 66 | 0
[18 empty] | 67 | 0
[18 empty] | 68 | 0
[18 empty] | 69 | 0
[18 empty] | 70 | 0
[18 empty] | 71 | 0
[18 empty] | 72 | 0
[18 empty] | 73 | 0
[18 empty] | 74 | 0
[18 empty] | 75 | 0
[18 empty] | 76 | 0
[18 empty] | 77 | 0
[18 empty] | 78 | 0
[18 empty] | 79 | 0
[18 empty] | 80 | 0
[18 empty] | 81 | 0
[18 empty] | 82 | 0
[18 empty] | 83 | 0
[18 empty] | 84 | 0
[18 empty] | 85 | 0
[18 empty] | 86 | 0
[18 empty] | 87 | 0
[18 empty] | 88 | 0
[18 empty] | 89 | 0
[18 empty] | 90 | 0
[18 empty] | 91 | 0
[18 empty] | 92 | 0
[18 empty] | 93 | 0
[18 empty] | 94 | 0
[18 empty] | 95 | 0
[18 empty] | 96 | 0
[18 empty] | 97 | 0
[18 empty] | 98 | 0
[18 empty] | 99 | 0
[18 empty] | 100 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  |  | Geothermal Wells Risk Matrix - GEO4ALL - Net Assessment | [14 empty] | 0 | 0
|  |  | Net Assessment Likelihood | [14 empty] | 0 | 0
|  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  | 5 | 6 | 7 | 8 | 0 | 0
| Net Assessment Impact | A | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | B | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | C | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | D | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | E | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | F | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | G | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
|  | H | [15 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
Increasing Likelihood
Increasing Impact
Purple risks are the most critical risks
White risks are the least important risks

## Lists (hidden)
Likelihood | Impact | Assessment Type | Instructions
1 | A | Worst Credible | Enter risks in Risk Register rows 7 onward.
2 | B | Net Assessment | Select likelihood 1-8 and impact A-H.
3 | C |  | Use Risk Matrix!B3 dropdown to switch Worst Credible / Net Assessment.
4 | D |  | Each likelihood/impact quadrant is a 5 x 5 mini-grid, allowing up to 25 risk numbers.
5 | E |  | Empty positions show the matrix zone color; risk numbers are displayed in blue text.
6 | F |  | Do not overwrite matrix formulas.
7 | G
8 | H